## Sheet1
Week Beginning | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17
| Common Words | Wav2Veq Research | Fine Tuning | Begin own architecture | Experimenting | Testing | Systems Week | Report Writing | Final Report | Project Compendium
| Embeddings | Wav2Veq Presentation | 2022-10-17 | Research | Start report writing |  |  | Poster
| Planning | Setup HASEL |  | Begin experiments
Wav2Veq initial